## Register
# | Risk Description | Cause/s | Description of Potential Consequences | Current Safeguards or Existing Controls | Initial Risk Assessment |  |  |  | Rating Rationale | Response | Proposed Action
[5 empty] | Likelihood | Consequence | Risk Rating | Risk Priority
1 | Personnel COVID 19 infections on site | 1. International staff returning to site that may be infected. | 1. COVID 19 medical treatment cases 2. Loss of productivity or total stoppages of operations in affected areas should an infection occur. 3. Reduced management capacity while senior staff take longer to get to site. | 1. Continued remote operation where feasible. 2. Managed process to return expats. 3. Operational area isolation from other. | Likely | Significant | 11 | High | International personnel working in isolation at home. | Avoid | 1. Prepare screening venue and screen returning personnel off-site before re-entering operation. 2. Formulate isolation and treatment procedure should a case arise. 2. Comply with government regulations for persons entering country. If there are further concerns, possibly enforce isolation for 2 weeks to detect any symptoms before integration with rest of the team.
|  | 2. Local personnel returning to site that may be infected. |  | 1. Continued remote operation where feasible. 2. Managed process to return local personnel. 3. Operational area isolation from other. | Very Unlikely | Significant | 6 | Medium | Country specific lockdown measures/regulations. | Mitigate | 1. Strictly limit personnel leaving the mine (GM approval and travel permit). 2. Strictly Limit personnel entering the mine (security checkpoint and GM approval) 3. Effective communication both onsite and offsite. 4. Implement control measures on site to limit the spread
|  | 3. Essential deliveries to site. |  | 1. Delivery acceptance process. | Unlikely | Significant | 9 | Significant | Controlled environment | Mitigate | 1. Strict hygienic measures for deliveries (E.g. masks, gloves, disinfect) 2. Isolate personnel receiving deliveries from construction personnel. 3. Disinfect items before removal from packaging.
|  | 4. Use of essential services outside mine (E.g. Banking) |  | 1. Fixed drivers used for town errands | Unlikely | Significant | 9 | Significant | Controlled environment | Transfer | 1. Strict hygienic measures for deliveries (E.g. masks, gloves, disinfect) 2. Restrict number of and isolate personnel going to town for essential services from construction personnel. 3. Disinfect items procured before handover to other personnel.
|  | 5. Personnel operating during lockdown returning home where infections may be much high or using transport with a high risk of transmission and then returning to site |  | 1. Continued remote operation where feasible. 2. Managed process to return expats/locals. 3. Operating area isolation from other. | Likely | Significant | 11 | High | Controlled environment | Avoid | 1. Incentivise longer site period without returning home.
2 | Personnel COVID 19 transmissions on site | 1. Asymptomatic infected personnel without symptoms spreading the disease. | 1. COVID 19 medical treatment cases 2. Loss of productivity or total stoppages of operations in affected areas should an infection occur. 3. Reduced management capacity for affected management personnel. | 1. Continued remote operation where feasible. 2. Managed process to return expats. 3. Operating area personnel isolation from other. | Unlikely | Significant | 9 | Significant | Controlled environment | Mitigate | 1. Testing of all personnel should a positive case be detected. 2. Use of fixed rotating teams (Management and operators) that are isolated from the other (I.e. Keep teams A and B away from the other should an infection occur that a team can be isolated.
|  | 2. Conditions on site may conducive to the spread of Covid-19 (E.g. Shared eating areas) |  |  | Very Likely | Significant | 12 | High | There are social areas that makes social distancing difficult. | Mitigate | 1. Queuing social distancing measures in eating halls. 2. Transport disinfection and enforced mask usage.
3 | COVID 19 medical treatment cases | 1. Personnel COVID 19 Infections on site | Could die if proper medical treatment is not available. | 1. Clinic | Unlikely | Significant | 9 | Significant |  | Mitigate | 1. Take to clinic in town. 2. Contact clinic to understand if it has a ventilator etc. and what their procedures are for taking on a COVID 19 case. 3. Evacuate/Take to closest COVID ready hospital.
4 | Restricted essential movements and services | 1. Lockdown restrictions | Personnel may not be able to address a personal crises leading to stress related risks. | 1. Support staff that can be reached via phone or VC to assist. | Likely | Not Ideal | 4 | Medium | Existing support structures in place. | Accept | 1. PM to have regular contact with Site team and home office team and assess situation on ongoing basis.
5 | [6 empty] | 0 | 0
6 | [6 empty] | 0 | 0
7 | [6 empty] | 0 | 0
8 | [6 empty] | 0 | 0
9 | [6 empty] | 0 | 0
10 | [6 empty] | 0 | 0
11 | [6 empty] | 0 | 0
12 | [6 empty] | 0 | 0
13 | [6 empty] | 0 | 0
14 | [6 empty] | 0 | 0
15 | [6 empty] | 0 | 0
16 | [6 empty] | 0 | 0
17 | [6 empty] | 0 | 0

## Responses
Risk Responses
Avoid | Avoid – Change plans to circumvent the problem;
Transfer | Transfer / share – Outsource risk (or a portion of the risk) to a third party or parties that can manage the outcome. This is done financially through insurance contracts or hedging transactions, or operationally through outsourcing an activity.
Mitigate | Control / mitigate / modify / reduce – Reduce threat impact or likelihood (or both) through intermediate steps;
Accept | Accept / retain – Assume the chance of the negative impact (or auto-insurance), eventually budget the cost (e.g. via a contingency budget line); or

## Risk Matrix
Impact
|  | NOT IDEAL | BIG | SIGNIFICANT
|  | Single Infection | Multiple Infections | Fatality | Health
|  | Week Delay | 2 Week Delay | Month Delay | Schedule
|  | $0.5m | $1m | >$1m | Cost
|  | Operation Constraints | Limited Operation | Site Closed | Legal
|  | Single Contractor | Two Contractors | All Site Personnel | Team Productivity Affected
|  | Project team awareness | Local area media awareness | National media awareness | Reputation
Likelihood | Very Likely 75 - 100% | 7 | 10 | 12
| Likely 50 - 75% | 4 | 8 | 11
| Unlikely 25 - 50% | 3 | 5 | 9
| Very Unlikely 0 - 25% | 1 | 2 | 6
Calls for Immediate Action
To be actioned in the coming month
To be actioned in the coming 3 Months
If and when….

## Ref (hidden)
IMPACT
|  | Not Ideal | Big | Significant
|  | 1 | 2 | 3
LIKELIHOOD | Very Likely | 7 | 10 | 12
| Likely | 4 | 8 | 11
| Unlikely | 3 | 5 | 9
| Very Unlikely | 1 | 2 | 6
Priority
1 | Low
2 | Low
3 | Low
4 | Medium
5 | Medium
6 | Medium
7 | Significant
8 | Significant
9 | Significant
10 | High
11 | High
12 | High